## School Action Plan
Objectives | Action Steps | Resources Required | Deliverables | Responsible Person | Priority | Deadline | Status | Challenges Encountered | Notes
Outcome #1- Increase utilization of federal food assistance programs in and after school by students.
Outcome #2- Increase utilization of direct food distributions by students and families.
Outcome #3- Increase utilization of SNAP among students’ families.
Outcome #4- New and/or improved food and nutrition resources available to students and families through community partners.

## School Action Plan with example
Objectives | Action Steps | Resources Required | Deliverables | Responsible Person | Priority | Deadline | Status | Challenges Encountered | Notes
Outcome #1- Increase utilization of federal food assistance programs in and after school by students.
Determine programs with most room for impact to focus on | Create baseline data of FAP utilization | data from schools & MDE | data graph | Rebecca | H | 2015-05-15 | In progress
| Review utilization data and which programs are in operation | baseline data | decision made | Rebecca & school staff | H | 2015-06-15 | Pending
| School staff & admin discussion | meeting | decision made | school staff | H | 2015-08-30 | Pending | challenging to schedule a time for teachers to meet, busy time of year. Also unsure of who should be at the table
Develop plan for increasing use of SBP | Create outreach materials for parents | examples materials | printed outreach materials | Rebecca & school staff | M | 2015-10-01 | Not started |  | School will tailor information and provide translation
| Evaluate current process for possible changes | site visit | notes & reccomendations | Rebecca | H | 2015-10-15 | Scheduled |  | A school staff to take part in the process will be helpful
| Solicit student feedback | survey | survey results | Rebecca-survey creation & school staff- administer survey | H | 2015-10-15 | pending
Outcome #2- Increase utilization of direct food distributions by students and families.
Determine distribution methods | review models with school | meeting, site tour | decision made | Sarah | M | 2015-05-15 | Scheduled
| School staff & admin discussion | meeting | decision made | school admin | H | 2015-06-30 | Pending
Organize 1st distribution | School staff determine date & time |  | decision made | school admin | H | 2015-08-30 | Not started
| School staff place order |  | order placed | school admin | M | 2015-09-05 | Not started
| Distribution outreach | flier creation & distribution | outreach takes place | school admin | M | 2015-09-05 | Not started
Outcome #3- Increase utilization of SNAP among students’ families.
Get baseline SNAP data | school data collection | school SNAP data | share data | school admin | H | 2015-07-01 | Pending
| meeting b/t SNAPO team & school | baseline SNAP data | plan developed | SNAPO & school | M | 2015-07-30 | Scheduled
| determine outreach focus | meeting | plan developed | SNAPO & school | M | 2015-07-30 | Scheduled
| Schedule outreach events | phone call | events scheduled | SNAPO & school | M | 2015-09-01
Outcome #4- New and/or improved food and nutrition resources available to students and families through community partners.
Determine baseline community partnerships & opportunities | Create list of exisiting resources through partners | phone call/meeting | comprehensive list | school admin | H | 2015-05-30 | Pending
Determine resources needed | Find gaps in resources available, determine potential partners | list of resource, meeting | action plan | school admin, S/R | M | 2015-06-30 | Not started
| Reach out to potential partners | phone calls, meetings | commitments | school admin, S/R | M | 2015-09-01 | Not started
Plan & prep new resources | Develop plans to fill gaps | phone calls, meetings | events scheduled | school admin & partners | M | 2015-10-30 | Not started